# InternLink — Development Plan

Completed Work + 12-Week Development Roadmap

| Project details |  |
| --- | --- |
| Date | August 31, 2026 |
| Timeline | 16 Weeks (Completed + 12 Weeks: Sep 1 — Nov 23, 2026) |
| Goal | Complete all missing features to match the project synopsis |

# 1. Current Status

| Module | Completion |
| --- | --- |
| Student Module | ~70% |
| Company Module | ~10% |
| Admin Module | ~5% |
| Application Module | ~40% |
| Interview Module | 0% |
| Resume Module | 0% |
| Overall | ~40–45% |

# 2. Completed Work

## WEEK -4 (Week 4 of Development) — Core UI & Landing

Pages

☑ Create landing page (index.jsp) with hero section, features, stats

☑ Create browseInternships.jsp with sidebar filters and AJAX loading

☑ Create applyInternship.jsp with detail view and apply button

☑ Create student/register.jsp with form validation

☑ Create student/login.jsp with authentication UI

☑ Create student/dashboard.jsp with sidebar navigation and metric

cards

☑ Create company/register.jsp form UI

☑ Create company/login.jsp form UI

☑ Create admin/login.jsp placeholder

☑ Build dark glassmorphism theme (style.css, dark-theme.css)

☑ Integrate Tailwind CSS, Google Fonts, Material Symbols

Deliverable:

All frontend UI pages created with responsive dark

theme.

## WEEK -3 (Week 3 of Development) — Database & Core

Models

☑ Set up Maven project with Jakarta EE 11, MySQL Connector, Gson

☑ Create DBConnection.java utility (JDBC to MySQL)

☑ Create Student.java model

☑ Create Internship.java model

☑ Create Bookmark.java model

☑ Create Application.java model

☑ Create StudentDAO.java (register, login, getById)

☑ Create InternshipDAO.java (search, getById, count)

☑ Create BookmarkDAO.java (add, remove, isBookmarked,

getBookmarkedIds)

☑ Create ApplicationDAO.java (apply, hasApplied)

☑ Create persistence.xml and context.xml

☑ Configure web.xml and beans.xml

Deliverable:

Database layer and all core models/DAOs ready.

## WEEK -2 (Week 2 of Development) — Student Backend &

Authentication

☑ Build StudentRegisterServlet — handles registration with validation

☑ Build StudentLoginServlet — handles authentication with session

management

☑ Implement password handling and session tracking

☑ Add form validation (email format, phone, password strength)

☑ Test student registration and login flow

Deliverable:

Students can register, log in, and maintain

sessions.

## WEEK -1 (Week 1 of Development) — Internship Browsing

& Applications

☑ Build InternshipServlet — JSON API with filters (keyword, category,

location, duration, stipend, pagination)

☑ Build BookmarkServlet — AJAX toggle (add/remove) with login check

☑ Build ApplicationServlet — submit application with duplicate

prevention

☑ Implement debounced search on browse page

☑ Implement active filter display and pagination (load more)

☑ Implement bookmark toggle with DOM updates and toast notifications

☑ Add success overlay and already-applied detection on apply page

Deliverable:

Full student workflow — browse, search, filter,

apply, bookmark.

# 3. Remaining Work — Weekly Task Plan

## WEEK 1 (Sep 1 — Sep 7) — Foundation: Database & Models

☑  Create complete db-schema.sql (all 5 tables: students, companies,

internships, applications, admins)

☑  Create Company.java model

☑  Create Admin.java model

☑  Create Interview.java model

☑  Create CompanyDAO.java (register, login, getById, update, getAll)

☑  Create AdminDAO.java (login, getById, getAllStudents,

getAllCompanies, verifyCompany, deleteCompany)

Deliverable:

Database foundation ready, all models and DAOs

created.

## WEEK 2 (Sep 8 — Sep 14) — Company Authentication

☑  Build CompanyRegisterServlet

☑  Build CompanyLoginServlet

☑  Fix company/register.jsp form action to submit to servlet

☑  Fix company/login.jsp form action to submit to servlet

☑  Create CompanyDAO.register() and authenticate() methods

☑  Test company registration and login flow end-to-end

Deliverable:

Companies can register and log in.

## WEEK 3 (Sep 15 — Sep 21) — Company Dashboard & Profile

☑  Create company/dashboard.jsp with metrics (total postings, total

applications, pending reviews)

☑  Create company/profile.jsp for viewing/editing company profile

☑  Build CompanyProfileServlet (view + update profile)

☑  Add CompanyDAO.updateCompany() method

☑  Style company pages to match existing dark theme

Deliverable:

Companies have a working dashboard and profile

management.

## WEEK 4 (Sep 22 — Sep 28) — Post & Manage Internships

☑  Create company/postInternship.jsp form

☑  Build PostInternshipServlet (create new listing)

☑  Build EditInternshipServlet (update existing listing)

☑  Build DeleteInternshipServlet

☑  Add InternshipDAO.insert(), update(), delete(), getByCompanyId()

methods

☑  Add "My Postings" section to company dashboard

Deliverable:

Companies can post, edit, and delete internship

listings.

## WEEK 5 (Sep 29 — Oct 5) — Application Review & Status

Management

☑  Create company/reviewApplications.jsp — list all applicants for

company’s internships

☑  Build ReviewApplicationsServlet

☑  Build UpdateApplicationStatusServlet (shortlist/reject/select)

☑  Add ApplicationDAO.updateStatus(), getApplicationsByCompanyId()

☑  Add status badges and action buttons (Shortlist/Reject)

Deliverable:

Companies can review applications and update

status.

## WEEK 6 (Oct 6 — Oct 12) — Admin Authentication &

Dashboard

☐ Fix admin/login.jsp — build proper login form

☐ Build AdminLoginServlet

☐ Create admin/dashboard.jsp with overview metrics (total students,

companies, internships, applications)

☐ Build AdminDashboardServlet

☐ Add AdminDAO methods for dashboard statistics

Deliverable:

Admin can log in and see system overview.

## WEEK 7 (Oct 13 — Oct 19) — Admin: Manage Students &

Companies

☐ Create admin/manageStudents.jsp — list all students with edit/delete

☐ Create admin/manageCompanies.jsp — list companies with verify/reject

☐ Build ManageStudentsServlet (list, edit, delete)

☐ Build ManageCompaniesServlet (list, verify, reject, delete)

☐ Add AdminDAO.deleteStudent(), verifyCompany(), rejectCompany()

Deliverable:

Admin can manage all student and company accounts.

## WEEK 8 (Oct 20 — Oct 26) — Admin: Manage Internships &

Applications

☐ Create admin/manageInternships.jsp — approve/remove postings

☐ Create admin/viewApplications.jsp — view all applications

☐ Build ManageInternshipsServlet

☐ Build ViewApplicationsServlet

☐ Add AdminDAO.approveInternship(), deleteInternship()

Deliverable:

Admin can moderate internships and view all

applications.

## WEEK 9 (Oct 27 — Nov 2) — Admin Reports & Student

Dashboard Fix

☐ Create admin/reports.jsp — placement statistics, charts

☐ Build ReportsServlet

☑  Make student/dashboard.jsp dynamic — fetch real data from DB

☑  Build StudentDashboardServlet

☑  Add ApplicationDAO.getApplicationsByStudent(), count by status

Deliverable:

Admin reports working, student dashboard shows real

data.

## WEEK 10 (Nov 3 — Nov 9) — Student Profile, Resume &

Status Tracking

☐ Create student/profile.jsp — view and edit profile

☐ Build StudentProfileServlet

☐ Add StudentDAO.updateStudent()

☐ Add Resume Upload feature (file upload servlet + storage)

☐ Create student/myApplications.jsp — view application status

☐ Build MyApplicationsServlet

Deliverable:

Students can edit profile, upload resume, and track

applications.

## WEEK 11 (Nov 10 — Nov 16) — Interview Scheduling

☑  Create Interview.java model (if not done in Week 1)

☐ Create InterviewDAO.java (schedule, update, getByCompanyId,

getByStudentId)

☐ Create company/scheduleInterview.jsp

☐ Create student/interviews.jsp — view scheduled interviews

☐ Build ScheduleInterviewServlet

☐ Add interview status to application workflow

Deliverable:

Full interview scheduling system working.

## WEEK 12 (Nov 17 — Nov 23) — Testing, Bug Fixes & Final

Polish

☐ End-to-end testing of all 3 roles (Student, Company, Admin)

☑  Fix any bugs found during testing

☐ Ensure all pages are responsive and match dark theme

☐ Add proper error handling and validation messages

☐ Test all AJAX endpoints (bookmarks, search, filters)

☐ Final cleanup — remove hardcoded data, fix TODOs

☐ Verify all synopsis requirements are met

Deliverable:

Complete, tested, polished InternLink portal

matching the synopsis.

# 4. Missing Features Checklist

## Not Implemented

☐ Resume Upload

☑  Company Profile Management

☑  Post Internships

☑  Edit/Delete Internships

☑  Company Recruitment Dashboard

☑  Application Review

☑  Shortlist Candidates

☑  Reject Applications

☐ Interview Scheduling

☐ Admin Login (functional)

☐ Admin Dashboard

☐ Manage Student Accounts

☐ Manage Company Accounts

☐ Approve/Remove Postings

☐ Report Generation

☐ Company Verification/Approval Workflow

☑  CompanyDAO

☑  AdminDAO

☑  Company Model

☑  Admin Model

☑  Companies Table

☑  Admins Table

## Partially Implemented

☑  Student Dashboard (UI only, static data)

☑  Company Registration (UI only, no backend)

☑  Company Login (UI only, no backend)

☑  Application Status Tracking (DB field exists, no UI)

☐ Student Profile Update (DAO method missing)

☑  DB Schema (only bookmarks table defined)

# 5. Priority Order

| Phase | Weeks | Result |
| --- | --- | --- |
| Phase 1: DB + Models + DAOs | 1 | Foundation ready |
| Phase 2: Company Auth | 2 | Companies can access portal |
| Phase 3: Company Dashboard + Profile | 3 | Full company profile management |
| Phase 4: Post Internships | 4 | Companies can create listings |
| Phase 5: Review Applications | 5 | Recruitment workflow complete |
| Phase 6: Admin Auth + Dashboard | 6 | Full admin access |
| Phase 7: Admin Management | 7?8 | Admin controls everything |
| Phase 8: Student Dashboard + Profile | 9?10 | Complete student experience |
| Phase 9: Interviews | 11 | Interview scheduling |
| Phase 10: Testing + Polish | 12 | Production-ready system |

# 6. Tech Stack (Current)

| Layer | Technology |
| --- | --- |
| Backend | Java 21/25, Jakarta EE 11 (Servlets, JSP, CDI) |
| Server | Apache Tomcat 11 |
| Database | MySQL 9.3 |
| Frontend | JSP, Tailwind CSS, Vanilla JavaScript |
| Build | Maven (WAR artifact) |

# 7. Development Notes

All new pages must follow the existing dark glassmorphism theme.

All servlets should use Gson for JSON responses.

Follow existing DAO pattern (JDBC, PreparedStatement).

Test each feature end-to-end before moving to next week.

Keep db-schema.sql updated with any schema changes.